## Sprint-1
Week #1 (7 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2022-10-07 | 2022-10-08 | 2022-10-09 | 2022-10-10 | 2022-10-11 | 2022-10-12 | 2022-10-13
28
Initial Understanding of requirements and set up | Environment Set up (DJango, Postman, VS Code, SQLite, Git | All | 4 | 4 | 3 | 2 | 1 | 1 | 1 | 0
| Requirement Analysis | All | 6 | 6 | 5 | 5 | 4 | 2 | 1 | 0
| Architecture Diagram | All | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0
| Learning and knowledge transfer of Django | All | 4 | 4 | 3 | 3 | 2 | 1 | 1 | 0
| Learning and KT of React JS | All | 4 | 4 | 4 | 4 | 3 | 3 | 2 | 0
| Learning and KT of SQLite | All | 4 | 4 | 3 | 3 | 2 | 2 | 1 | 0 | 2022-10-07 | 2022-10-08 | 2022-10-09 | 2022-10-10 | 2022-10-11 | 2022-10-12 | 2022-10-13
| Learning and KT of Postman | All | 4 | 4 | 4 | 3 | 3 | 2 | 1 | 0
|  | Total | 28 | 28 | 24 | 23 | 17 | 13 | 8 | 0
|  | Ideal | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0
Team:
Shanmukh | 7 hours / Week
Sree Harsha | 7 hours / Week
Prithvi Raj | 7 hours / Week
Roopa | 7 hours / Week
Total Available Hours During Sprint: | 28
XP Values followed | Communication
Sit Together
Simplicity
Established strong communication since the beginning of the project, We communicated individual strengths and experience about particular technologies and used it to decide our technology stack
We have kept our components modular and design simple so that it is easier to maintain, support, and revise.

## Sprint-2
Week #2 (7 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2022-10-14 | 2022-10-15 | 2022-10-16 | 2022-10-17 | 2022-10-18 | 2022-10-19 | 2022-10-20
28
Application Flow and Database Design | Class Diagram | All | 8 | 8 | 5 | 4 | 2 | 0 | 0 | 0
| Design Database Schema | All | 8 | 8 | 6 | 6 | 5 | 3 | 1 | 0
| Application flow | All | 8 | 8 | 8 | 6 | 6 | 4 | 2 | 0
| UI pages determinitation | All | 4 | 4 | 4 | 4 | 3 | 3 | 2 | 2
|  | Total | 28 | 28 | 23 | 20 | 16 | 10 | 5 | 2
Team: |  | Ideal | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0
Shanmukh | 7 hours / Week
Sree Harsha | 7 hours / Week
Prithvi Raj | 7 hours / Week
Roopa | 7 hours / Week
Total Available Hours During Sprint: | 28
XP Values followed | Communication
Sit Together
Simplicity

## Sprint-3
Week #3 (7 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2022-10-21 | 2022-10-22 | 2022-10-23 | 2022-10-24 | 2022-10-25 | 2022-10-26 | 2022-10-27
28
Database Design, Wireframes, API | Created Wireframe for landing page | Roopa | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 0
| Created Wireframes for Home, Login | Roopa | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0
| Created Wireframe for bookings page | Roopa | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0
| Populate flight with post flight api | Sree Harsha | 4 | 4 | 3 | 2 | 1 | 1 | 0 | 0
| Add authentication token with jwt | Sree Harsha | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0
| Create login API | Sree Harsha | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Create Employee api | Shanmukh | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0
| Add get flight detail api to fetch flight details | Shanmukh | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0
| Created Database Table for User,Airline,Booking,Flights,Gate Details | Shanmukh | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0
| Implement Landing page Nav bar. | Prithvi Raj | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0
| Implement Routing to Landing page and login page. | Prithvi Raj | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Implement custom button components that are used through out the application. | Prithvi Raj | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0
| Implement custom component (To use throughout the application) | Prithvi Raj | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0
|  | Total | 28 | 28 | 24 | 19 | 13 | 7 | 4 | 0
|  | Ideal | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0
Team:
Shanmukh | 7 hours / Week
Sree Harsha | 7 hours / Week
Prithvi Raj | 7 hours / Week
Roopa | 7 hours / Week
Total Available Hours During Sprint: | 28
XP Values followed | Communication
Sit Together
Simplicity

## Sprint-4
Week #4 (7 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2022-10-22 | 2022-10-23 | 2022-10-24 | 2022-10-25 | 2022-10-26 | 2022-10-27 | 2022-10-28
28
Setup Frontend Code, Routing, and API | Created Initial routing setup | Prithvi Raj | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Configure Redux flow in the application. | Prithvi Raj | 3 | 3 | 2 | 1 | 1 | 0 | 0 | 0
| Created Frontend Code setup | Prithvi Raj | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0
| Implement Landing page UI | Harsha | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Implement custom Text field component (To use throughout the application) | Harsha | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Get Flight Details from Backend API and Display on the UI accordingly | Harsha | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0
| Implement Application Navbar | Harsha | 3 | 3 | 2 | 1 | 1 | 0 | 0 | 0
| Implement custom Date Picker (to use throughout the application). | Shanmukh | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0
| Implement Retreive flight arrivals | Shanmukh | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
| Implement Retreive flight arrivals | Shanmukh | 3 | 3 | 2 | 1 | 1 | 0 | 0 | 0
| Created Wireframe for Login page | Roopa | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0
| Created Wireframe for information page | Roopa | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 0
| Create Update users API | Roopa | 3 | 3 | 2 | 2 | 1 | 1 | 0 | 0
|  | Total | 28 | 28 | 24 | 19 | 17 | 12 | 8 | 0
Team: |  | Ideal | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0
Shanmukh | 7 hours / Week
Sree Harsha | 7 hours / Week
Prithvi Raj | 7 hours / Week
Roopa | 7 hours / Week
Total Available Hours During Sprint: | 28
XP Values followed | Communication
Sit Together
Simplicity

## Sprint-5
Week #5 (7 hrs / week)
Backlog Item |  | Task Owner | Initial Estimate (Total Sprint Hours = 7 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2022-11-04 | 2022-11-05 | 2022-11-06 | 2022-11-07 | 2022-11-08 | 2022-11-09 | 2022-11-10
28
Development front end and API | Adding remaining side bar routes, and boilerplate navigation code for them. | Prithvi | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0
| Implementing landing page boilerplate for airport employee | Prithvi | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0
| Implement Application Employee Nav bar | Prithvi | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Implement Sidebar for routing with in Customer Persona and Employee persona | Prithvi | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
| Implement airline emp page | Harsha | 3 | 3 | 3 | 3 | 2 | 1 | 0 | 0
| Store details for login | Harsha | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Post login details to backend API from axios api call in frontend | Harsha | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 0
| Implement get airline details api | Shanmukh | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0
| Implement update airline details api | Shanmukh | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0
| Create Gate API | Shanmukh | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0
| Implement get Employee profile details api | Roopa | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1
| Create GetUsers API | Roopa | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Implement Airline Profile page for Customer | Roopa | 4 | 4 | 4 | 3 | 1 | 0 | 0 | 0
|  | Total | 28 | 28 | 23 | 18 | 12 | 9 | 4 | 1
|  | Ideal | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0
Team:
Shanmukh | 7 hours / Week
Sree Harsha | 7 hours / Week
Prithvi Raj | 7 hours / Week
Roopa | 7 hours / Week
Total Available Hours During Sprint: | 28
XP Values followed | Communication
Sit Together
Simplicity

## Sprint-6
Week #6 (7 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2022-11-11 | 2022-11-12 | 2022-11-13 | 2022-11-14 | 2022-11-15 | 2022-11-16 | 2022-11-17
28
Development front end and API | Implement Airline Profile Page for Employee | Roopa | 4 | 4 | 4 | 4 | 3 | 2 | 1 | 1
| Create reducers actions for Airline Details | Roopa | 3 | 3 | 2 | 1 | 1 | 0 | 0 | 0
| Implement airline Employee Profile edit dialog component | Harsha | 2.5 | 2.5 | 1 | 1 | 1 | 1 | 1 | 0
| Implement airport employee Profile edit Dialog component | Harsha | 2.5 | 2.5 | 2.5 | 1.5 | 0.5 | 0 | 0 | 0
| Updated Model for flights (Added new fields) | Shanmukh | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
| Implement update Baggage claim api | Shanmukh | 3 | 3 | 3 | 2 | 2 | 2 | 1 | 0
| Implement post api for Gate confirmation | Shanmukh | 3.5 | 3.5 | 3 | 3 | 1 | 0 | 0 | 0
| Implement get flight details api | Harsha | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0
| Implement Gate assignment Functionality | Prithvi | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 0
| Implement view flight details Page | Prithvi | 4 | 4 | 2 | 2 | 2 | 2 | 0 | 0
|  | Total | 28 | 28 | 22.5 | 17.5 | 13.5 | 8 | 4 | 1
|  | Ideal | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0
Team:
Shanmukh | 7 hours / Week
Sree Harsha | 7 hours / Week
Prithvi Raj | 7 hours / Week
Roopa | 7 hours / Week
Total Available Hours During Sprint: | 28
XP Values followed | Communication
Sit Together
Simplicity

## Sprint-7
Week #7 (7 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2022-11-18 | 2022-11-19 | 2022-11-20 | 2022-11-21 | 2022-11-22 | 2022-11-23 | 2022-11-24
28
Development front end and API | Implement view bookings page | Prithvi | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0
| Implement booking details selection dialog | Prithvi | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0
| Implement Payment confirmation Page | Prithvi | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
| Implement Cancel booking api Functionality | Harsha | 1.5 | 1.5 | 0.5 | 0 | 0 | 0 | 0 | 0
| Create member and Flight Modules | Harsha | 3 | 3 | 3 | 2 | 1 | 1 | 0 | 0
| Implement and test airline flights | Harsha | 1.5 | 1.5 | 1.5 | 1.5 | 1 | 1 | 1 | 0
| Implement add flight API | Shanmukh | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Created Dashboard API for departing flights | Shanmukh | 1.5 | 1.5 | 1.5 | 1.5 | 1 | 1 | 1 | 0
| Implement View Bookings API | Shanmukh | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0
| Implement getFlights for customer api | Shanmukh | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2 | 0 | 0
| Implement update dialog in Airline profile Page | Roopa | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0
| UI change in Airline Profile Page for Customer | Roopa | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Implement Airline Profile Page for Employee | Roopa | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 0
|  | Total | 28 | 28 | 23 | 19.5 | 13.5 | 8 | 4 | 0
|  | Ideal | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0
Team:
Shanmukh | 7 hours / Week
Sree Harsha | 7 hours / Week
Prithvi Raj | 7 hours / Week
Roopa | 7 hours / Week
Total Available Hours During Sprint: | 28
XP Values followed | Communication
Sit Together
Simplicity

## Sprint-8
Week #7 (7 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x 4) | D1 | D2 | D3 | D4 | D5 | D6
|  |  |  | 2022-11-25 | 2022-11-26 | 2022-11-27 | 2022-11-28 | 2022-11-29 | 2022-11-30
28
Deployment + Testing | API on Automatic gate assignment | Prithvi | 2 | 2 | 0 | 0 | 0 | 0 | 0
| Scripts for Deployment | ALL | 7 | 5 | 3 | 1 | 0 | 0 | 0
| Validation check throughout application | ALL | 7 | 7 | 6 | 5 | 4 | 3 | 2
| Testing all flows and data | ALL | 7 | 7 | 6 | 6 | 4 | 4 | 2
| Merge Conflicts and integration issues | ALL | 5 | 5 | 5 | 3 | 2 | 0 | 0
|  | Total | 28 | 26 | 20 | 15 | 10 | 7 | 4
|  | Ideal | 28 | 24 | 20 | 16 | 12 | 8 | 4
Team:
Shanmukh | 7 hours / Week
Sree Harsha | 7 hours / Week
Prithvi Raj | 7 hours / Week
Roopa | 7 hours / Week
Total Available Hours During Sprint: | 28
XP Values followed | Communication
Sit Together
Simplicity

## Retrospective-Sprint-Sheet
Retrospective Report for Sprint-1
No. | Agenda | What Went Well | What didnt go well | Remaining questions/ Should work on
1 | Database selection | We came up with the most scalable db for our project by choosing SQLite | We individually came up with different database solutions. Had we discussed together, it would have taken less time and avoided redundancy. | Vague understanding of UI Design and Wireframes
2 | Backend Tech selection | As few of us had worked previously with DJango, KT was efficient and it was a wise choice to select it for backend implementation. | Sync Up was difficult as all of us had different schedules
3 | Frontend Tech Selection | Given the features provided by react for single page applications, we agreed to learn and implement React.js for our frontend | Agreeing on common tech stack was difficult.
Retrospective Report for Sprint - 2
No. | Agenda | What Went Well | What didnt go well | Remaining questions/ Should work on
1 | Class Diagram | Understood different components interactions and designed the class Diagram
2 | Design Database Schema | Finalized the DB tables | It's been difficult to figure out the exact schemas.
3 | Application flow and System Design | Worked on the initial routing setup, landing page boilerplate code. | It took some time to determine which component would be crucial and how component interaction could be done | Handling the states
Retrospective Report for Sprint - 3
No. | Agenda | What Went Well | What didnt go well | Remaining questions/ Should work on
1 | Wireframes | Created wireframes for landing,search, login and singup pages | Reworked on few screens for the ease of developement of controls and better viewing. | Figuring out the design for the remaning screens
2 | API | Implemented Backend dependencies, authentication and error handling
3 | Frontend Implementation | Developed the initial routing setup, navigation bar for employee and customer and custom UI controls to use overall application |  | How to handle the States thorughout the application
Retrospective Report for Sprint - 4
No. | Agenda | What Went Well | What didnt go well | Remaining questions/ Should work on
1 | Frontend Implementation | Implemented the Initial redux setup and landing page UI | Due to mis commit we had to rework on a component
2 | API | Implemented FlightDetails, get and update Gate details API calls
3 | Wireframes | Created wireframes for Login and flight screens | Finalized the UI screens
Retrospective Report for Sprint - 5
No. | Agenda | What Went Well | What didnt go well | Remaining questions/ Should work on
1 | Frontend Implementation | integration with code flow took less time than expected
2 | API |  | Reworked on Booking schema as we have to add the new fields in it. | Need to cross check the fields included in all the schemas
Retrospective Report for Sprint - 6
No. | Agenda | What Went Well | What didnt go well | Remaining questions/ Should work on
1 | Frontend Implementation |  | Requirement changes cost some extra time for Airline profile ui part
2 | API | Successful profile apis flow for customer and employee
3
Retrospective Report for Sprint - 7
No. | Agenda | What Went Well | What didnt go well | Remaining questions/ Should work on
1 | Frontend Implementation | Finished the major components in the application like Booking
2 | API | Implemented Cancel, Change Booking, Purchase seats and get available seats APIs | Frontend and api logics for booking were not in sync initially due to different understnading of requirement. so wasted few hours fixing it.
Retrospective Report for Sprint - 8
No. | Agenda | What Went Well | What didnt go well | Remaining questions/ Should work on
1 | Merge Conflicts and integration issues | Completely done with integration and resolved all the issues | Lot of Code conflicts, by not taking latest pull from Master branch
2 | Deployment | Successfully deployed to an EC2 Autoscale cluster |  | More about configuring secuirty policies
3 | Testing | Multiple tests with different results and system conditions. | As expected
4 | Retrospection | Everything was reviewed, from the beginning to the conclusion, initial goals and final accomplishments, challenges, how to resolve. |  | We are confident that we met our expectations 95% of the time.